## Requirements Register
BVDRS ¦ Requirements Register
Authoritative working register for the assessment. F = Functional; NF = Non-functional. NFR priorities are provisional BA recommendations (Must/Should/Could), not stakeholder approvals; numeric targets and conditional designs remain subject to validation. Sources distinguish assessment evidence from proposed controls.
Requirement ID | Module | Description / Requirement | Type (F/NF) | Priority | Source / Stakeholder / Basis | Acceptance Criteria / Verification | Status | Related Objective(s) | Open Issue(s) | BA Notes
FR-DET-001 | Imagery ingestion & candidate detection | Register each imagery delivery with source, acquisition date, resolution, coverage, coordinate reference, and import outcome. | F | Must | Assessment §2.2.A — quarterly 50 cm imagery and manual comparison; proposed control to register image provenance. Weekly imagery is not assumed. | The register shows these fields for every imported scene and records a validation failure where required metadata is absent. | Proposed | BO-01 | —
FR-DET-002 | Imagery ingestion & candidate detection | Validate the submitted image file and basic metadata before adding it to the accepted comparison baseline. | F | Must | Assessment §2.2.A — imagery comparison is currently manual; proposed pre-ingestion validation is a data-quality control, not an existing capability. | A user can see rejected/accepted status and a reason; a rejected image cannot silently replace the prior baseline. | Proposed | BO-01 | —
FR-DET-003 | Imagery ingestion & candidate detection | Support comparison of an accepted image with a selected earlier image to identify candidate changes. | F | Should | Eng. Hesham requests automated detection; Eng. Ahmed identifies quarterly imagery and contract/budget constraints (Assessment §§2.2.A, 2.5). Automation is proposed; cadence/SLA remain unresolved. | The analyst can choose the comparison pair and view candidate outputs tied to both source images. No processing-time SLA is assumed. | Proposed | BO-01 | —
FR-DET-004 | Imagery ingestion & candidate detection | Allow GIS analysts to confirm, dismiss, or amend each candidate before it becomes an inspection ticket. | F | Must | Assessment §2.2.A / GIS current practice — analysts identify suspected changes before field dispatch; analyst confirm/dismiss control is proposed. | Every candidate has a review status, reviewer, timestamp, and retained reason for dismissal/amendment. | Proposed | BO-01 | —
FR-DET-005 | Imagery ingestion & candidate detection | Create an inspection ticket from a confirmed candidate and link it to the source images and map location. | F | Must | Assessment §2.2.A — suspected sites are currently dispatched to engineering offices by paper maps/reports; digital ticket creation is proposed. | The ticket identifies its source candidate, current status, district/assignment where known, and associated evidence. | Proposed | BO-01 | —
FR-FLD-001 | Field inspection & evidence | Present assigned inspection tickets to the authorised engineer, with the site description and available map evidence. | F | Must | Eng. Mona, Assessment §2.5 — no decision without an engineer site visit; assigned-ticket view is a proposed workflow aid, not an inspection exemption. | An engineer sees only tickets assigned or otherwise authorised for their role and can open the linked evidence. | Proposed | BO-01; BO-03; BO-06 | —
FR-FLD-002 | Field inspection & evidence | Capture the visit outcome, inspection date, inspector, notes, estimated violating area, and any reason the site could not be located. | F | Must | Assessment §2.2.A — engineers visit sites, write a Mahdar, estimate area and record site findings; structured digital fields are proposed. | The inspection record cannot be submitted without the approved mandatory fields; an unable-to-locate outcome remains visible as unresolved. | Proposed | BO-01; BO-03; BO-06 | —
FR-FLD-003 | Field inspection & evidence | Allow supporting photographs and documents to be attached to the related ticket with available capture metadata. | F | Must | Assessment §2.2.A — field evidence includes photos taken with personal phones; controlled attachment linkage is proposed. Metadata is recorded only when available. | Each attachment is linked to a ticket and has an upload/capture timestamp; location metadata is recorded only when available and not fabricated. | Proposed | BO-01; BO-03; BO-06 | —
FR-FLD-004 | Field inspection & evidence | Support saving a field record when connectivity is unavailable and synchronising it after connectivity returns. | F | Should | Mr. Walid / field locations, Assessment §§2.3, 2.5 — village connectivity is unreliable; offline capture is proposed pending technical/security validation. | An offline test preserves a saved record; a retry does not create a duplicate; sync success/failure is visible. | Proposed | BO-01; BO-03; BO-06 | —
FR-FLD-005 | Field inspection & evidence | Record the central receipt/synchronisation state of each dispatched ticket and its inspection result. | F | Must | Assessment §2.2.A — field reports may not return to GIS and the proportion is unquantified; central receipt/synchronisation status is a proposed control. | The dashboard identifies completed, outstanding, returned, and sync-failed items; no missing-report rate is assumed. | Proposed | BO-01; BO-03; BO-06 | —
FR-APP-001 | Application intake & case record | Create a uniquely referenced case with applicant and, where relevant, authorised agent details. | F | Must | Assessment §2.2.B — applications are submitted on paper and registered in Excel; a unique digital case reference is proposed. | Each accepted registration receives a unique reference that is searchable and linked to its owner/agent record. | Proposed | BO-02; BO-03; BO-06 | —
FR-APP-002 | Application intake & case record | Record the application document checklist, including ownership documents, national ID, structural-safety report, photos, site sketch, and power of attorney where relevant. | F | Must | Assessment 2.2.B | The checklist displays each required item as received, missing, or needing review; applicable requirements are configurable only after approval. | Source-supported basis | BO-02; BO-03; BO-06 | —
FR-APP-003 | Application intake & case record | Record intake channel, registration timestamp, receiving centre/user, and receipt identifier. | F | Must | Assessment §2.2.B — intake is registered in Excel and includes deposit evidence; digital intake metadata is proposed, without resolving deposit timing/refund policy. | The case history displays the registration event and issuing office/user; paper receipts can be cross-referenced. | Proposed | BO-02; BO-03; BO-06 | —
FR-APP-004 | Application intake & case record | Record the building location as a map point and descriptive location information, with a flag for provisional/uncertain location. | F | Must | Eng. Mona, Assessment §2.5 — map-based applicant location could reduce site-finding time; Assessment §2.3 records unreliable/missing cadastral geometry. A map pin must not be labelled a verified parcel. | The record distinguishes a map pin from a verified cadastral parcel and captures the source/accuracy information available. | Proposed | BO-02; BO-03; BO-06 | —
FR-APP-005 | Application intake & case record | Record an application status and status-change history visible to authorised staff. | F | Must | Mr. Sayed, Assessment §2.5 — applicants return weekly asking about their file; status history is a proposed response to this visibility gap. | A user can view status, responsible role, timestamp, and outstanding action without relying on a separate local spreadsheet. | Proposed | BO-02; BO-03; BO-06 | —
FR-APP-006 | Application intake & case record | Support an assisted intake workflow and allow an online intake channel only when the channel is approved and available. | F | Should | Hesham vs Sayed; decision open OI-09 | A technical-centre user can register a case; portal integration is not represented as operational until access and scope are approved. | Needs decision / validation | BO-02; BO-03; BO-06 | OI-09
FR-GIS-001 | Spatial reference & screening | Maintain metadata for each reference layer, including owner/source, date, coordinate reference, coverage, and last update. | F | Must | Eng. Ahmed / Assessment §2.3 — coordinate systems differ and layers may be shifted by tens of metres; layer metadata and QA are proposed controls. | Layer metadata are viewable to authorised GIS users; unknown or stale metadata are flagged. | Proposed | BO-03 | —
FR-GIS-002 | Spatial reference & screening | Screen an application location against available, approved restriction layers: urban boundary, agricultural land, Nile protection, heritage, and airport height restrictions where applicable data are available. | F | Must | Mona / assessment 2.2.B | The result shows per-layer hit/no-hit/unknown, source date, and spatial query status; unavailable layers are not treated as a clear result. | Source-supported basis | BO-03 | —
FR-GIS-003 | Spatial reference & screening | Present spatial results as screening evidence for review, not as an automatic final legal or engineering decision. | F | Must | Analysis control based on Mona / Legal context | A case cannot be finally approved/rejected solely by an unreviewed spatial flag; authorised users record the final decision. | Proposed | BO-03 | —
FR-GIS-004 | Spatial reference & screening | Preserve source coordinate-reference metadata and record transformation method and QA results for migrated or transformed layers. | F | Must | Assessment 2.3; OI-04 | The data-load record identifies source and target references and logs the approved operation; unapproved transformations are blocked from production. | Needs decision / validation | BO-03 | OI-04
FR-GIS-005 | Spatial reference & screening | Support a provisional location reference where cadastral parcel geometry is unavailable or unreliable. | F | Should | Assessment 2.3; proposed | Users can locate and track a building without the system claiming that a provisional point is a certified parcel boundary. | Proposed | BO-03 | —
FR-WF-001 | Committee workflow & decisions | Maintain a committee review queue showing case reference, age, district, inspection status, completeness, and current decision stage. | F | Must | Assessment §2.2.B — three committees meet weekly and review about 80 files per meeting; the consolidated queue is a proposed visibility/control capability. | An authorised committee user can filter the queue and open a consistent case evidence pack. | Proposed | BO-02; BO-04; BO-07 | —
FR-WF-002 | Committee workflow & decisions | Record one of the stated decision outcomes: approve, reject, or request additional documents. | F | Must | Assessment 2.2.B | Every committee decision records the outcome, decision date, authorised decision-maker/committee, and any required reason. | Source-supported basis | BO-02; BO-04; BO-07 | —
FR-WF-003 | Committee workflow & decisions | Return a case requiring documents to an identified owner/queue with the outstanding items recorded. | F | Must | Assessment 2.2.B; routing OI-12 | A missing-document case displays the specific outstanding items; final routing and the resubmission review point are confirmed before configuration. | Needs decision / validation | BO-02; BO-04; BO-07 | OI-12
FR-WF-004 | Committee workflow & decisions | Preserve the case decision history and related evidence without overwriting prior outcomes. | F | Must | Assessment §2.2.B — committee outcomes move through paper and distributed Excel records; preserving decision history is a proposed audit control. | A reviewer can see prior status/decision events and the user/time associated with each change. | Proposed | BO-02; BO-04; BO-07 | —
FR-WF-005 | Committee workflow & decisions | Link each appeal record to the original case and record filing date, notification evidence, grounds/documents, and recorded outcome. | F | Should | Assessment 2.2.B; OI-07 | An appeal can be tracked separately and linked to the rejected case; no automatic stay or outcome is inferred. | Needs decision / validation | BO-02; BO-04; BO-07 | OI-07
FR-WF-006 | Committee workflow & decisions | Record authorised follow-up after a final decision, including formal-notice status where required by the approved process. | F | Should | Adel; proposed | A case shows whether the required follow-up has been recorded; the system does not autonomously issue or execute a removal decision. | Proposed | BO-02; BO-04; BO-07 | —
FR-FIN-001 | Fees, receipts & instalments | Maintain an approved, versioned tariff schedule with effective date, zone class, rate, approver, and supporting reference. | F | Must | Finance / assessment 2.4; proposed | A fee calculation can identify the exact tariff version and approval used. | Proposed | BO-05 | —
FR-FIN-002 | Fees, receipts & instalments | Support an approved special street rate that takes precedence over a general zone rate when the approval is valid. | F | Must | Finance note in assessment 2.4 | The calculation records the selected street/zone rate and approval reference; unapproved overrides cannot be used. | Source-supported basis | BO-05 | —
FR-FIN-003 | Fees, receipts & instalments | Prevent a payable amount from being finalised when no approved rate exists for the relevant extension area. | F | Must | Assessment 2.4; proposed control OI-05 | The case is marked pending pricing and no default rate is silently applied. | Needs decision / validation | BO-05 | OI-05
FR-FIN-004 | Fees, receipts & instalments | Calculate the fee from the accepted violating area and the applicable approved price per square metre. | F | Must | Assessment 2.2.B and 2.4 | The calculation displays area, rate source, arithmetic, and total; any manual area correction is attributed to an authorised user. | Source-supported basis | BO-05 | —
FR-FIN-005 | Fees, receipts & instalments | Record the 25% deposit/payment evidence and the approved remaining balance for each application. | F | Must | Assessment 2.4; refund/timing OI-06 | The case shows deposit amount, date, reference, balance, and any refund request/disposition; refund policy is not hard-coded while unresolved. | Needs decision / validation | BO-05 | OI-06
FR-FIN-006 | Fees, receipts & instalments | Track full payment or an authorised instalment arrangement of up to 36 months, including due dates and receipts. | F | Must | Assessment 2.4 | The ledger lists each amount due/paid and outstanding balance; extensions, penalties, reminders, or certificate suspension require separately approved rules. | Source-supported basis | BO-05 | —
FR-CERT-001 | Certificates & utility verification | Record a certificate identifier, issue date, issuing authority, and current status after the approved issuance conditions are met. | F | Must | Assessment 2.2.B; issuance rule OI-08 | The certificate record links to the case and records the approved issuance basis; exact issuance trigger must be approved. | Needs decision / validation | BO-05; BO-07 | OI-08
FR-CERT-002 | Certificates & utility verification | Retain the relationship between a certificate and the related application, decision, and relevant payment records. | F | Must | Assessment §2.2.B — certificates are printed/signed and paper copies are mailed to utilities; linking certificate, case, decision and payment history is a proposed control. | An authorised user can trace the certificate back to the source case and decision/payment history. | Proposed | BO-05; BO-07 | —
FR-CERT-003 | Certificates & utility verification | Support a utility verification interface only after an approved data-sharing/security design and counterpart agreement. | F | Could | Khaled / Walid; OI-09 | No live integration is assumed; a test interface must pass an agreed authorisation and minimal-data verification test before production. | Needs decision / validation | BO-05; BO-07 | OI-09
FR-REP-001 | Reports & dashboards | Provide a map-based dashboard for violations by district, application status/volume, collections, and recorded removals/follow-up. | F | Must | Hesham / assessment 2.5 | Each metric has a documented definition, source, refresh time, and permissions; removal figures reflect recorded authorised events only. | Source-supported basis | BO-04 | —
FR-REP-002 | Reports & dashboards | Provide operational queue reports for application age, committee throughput, missing documents, inspection outstanding items, and instalment balances. | F | Should | Assessment §§2.2.B, 2.3 — case status, committee work and finance data are handled through paper and distributed Excel; operational queue reporting is a proposed capability. | Filters reconcile to underlying case records and totals; the report does not imply unrecorded work is completed. | Proposed | BO-04 | —
FR-REP-003 | Reports & dashboards | Allow authorised users to export permitted report data and record the report date/filter context. | F | Could | BA proposal only: the assessment does not explicitly request general report export. Validate intended users, permitted fields and access rules before approval. | An authorised user can export an approved set of fields; access restrictions apply to sensitive personal data. | Proposed | BO-04 | —
FR-DAT-001 | Legacy data migration & reconciliation | Profile and map the source fields from Oracle 11g and local Excel files before migration. | F | Must | Assessment 2.3; proposed | The migration mapping lists each source field, transformation, mandatory rule, and exception outcome. | Proposed | BO-02; BO-03 | —
FR-DAT-002 | Legacy data migration & reconciliation | Reconcile source/target record counts and duplicates for each approved migration batch. | F | Must | Assessment §2.3 — Oracle 11g and ten distributed Excel sheets are in use; batch count/duplicate reconciliation is a proposed migration control. | A batch report lists read, loaded, rejected, duplicate, and exception counts and receives data-owner approval. | Proposed | BO-02; BO-03 | —
FR-DAT-003 | Legacy data migration & reconciliation | Apply an approved migration scope that distinguishes the approximately 38,000 pending applications from the approximately 40,000 paper archive files. | F | Must | OI-10 | The migration plan explicitly states which population is included and records the resolution of duplicate/overlapping records before loading. | Needs decision / validation | BO-02; BO-03 | OI-10
NFR-001 | Performance | Candidate target: standard case search and case summary render in no more than 3 seconds at the agreed pilot load and network conditions. | NF | Should | No numeric response-time SLA is stated in the source assessment. The 3-second value is only a candidate target proposed for validation with IT/business. | Record p95 response times in an agreed test; approve concurrency and sample volume first. | Needs decision / validation | BO-02; BO-04 | — | Provisional BA recommendation only; confirm with business/IT during prioritisation. The 3-second candidate target is not approved and must be validated under agreed pilot load/network conditions.
NFR-002 | Capacity | Candidate test volume: at least 50,000 active case records, based on the illustrative backlog-plus-intake calculation; document attachment volume remains to be sized. | NF | Must | Derived sizing hypothesis: 38,000 pending applications plus about 1,500 new/month over an illustrative six months gives about 47,000; 50,000 is a proposed test volume, not an approved capacity target. | Load representative records and measure search, storage, reports, and migration time. | Needs decision / validation | BO-02; BO-04 | — | Provisional BA recommendation only; confirm with business/IT. The 50,000-record figure is a candidate sizing assumption based on illustrative backlog maths, not an approved capacity target.
NFR-003 | Availability | Define availability against the Governorate's official working hours and planned maintenance window; agree a measurable monthly target before baseline. | NF | Should | Assessment §2.3 identifies weak internet at two centres and village locations; no availability percentage or official service-hours target is provided. | Monitoring report and agreed calculation formula. | Needs decision / validation | BO-06 | — | Provisional BA recommendation only; confirm with IT/service owner. The assessment gives no availability percentage or official service-hours target.
NFR-004 | Recovery | Approve Recovery Point Objective (RPO), Recovery Time Objective (RTO), backup frequency, retention, and restoration test schedule with IT. Do not assume values in this draft. | NF | Must | The assessment provides no RPO, RTO, backup frequency, retention duration or restore-time target; these require IT/risk-owner decisions. | Demonstrated restore test with recorded data-loss and restoration durations. | Needs decision / validation | BO-06; BO-07 | — | Provisional BA recommendation only; confirm with IT/risk owners. RPO, RTO, backup frequency, retention and restore targets remain undefined.
NFR-005 | Security / access | Enforce role-based permissions so only authorised roles may access applicant details, change decisions, edit tariffs, or view finance records. | NF | Must | Assessment §§2.2.B, 2.3 includes applicant IDs, ownership documents, safety reports and a data-residency constraint; RBAC is a proposed control requiring role validation. | Role/permission matrix and negative-access tests. | Needs decision / validation | BO-07 | — | Provisional BA recommendation only; confirm role matrix and data-access rules with IT/business. Exact roles are not approved in this workbook.
NFR-006 | Auditability | Record actor, timestamp, old/new status, reason, and reference for material changes to decisions, tariffs, case status, payment records, and certificate status. | NF | Must | Assessment §§2.2.B, 2.3 describes committee decisions, financial records and distributed paper/Excel handoffs; the detailed audit-event requirement is a proposed control. | Audit test against a defined set of material actions; historical events are retrievable. | Proposed | BO-07 | — | Provisional BA recommendation only; confirm the audit-event scope and retention with process owners/IT.
NFR-007 | Arabic usability | Support Arabic content and right-to-left presentation for citizen/staff interactions where Arabic is the chosen user language. | NF | Should | No explicit Arabic-interface requirement is stated in the assessment. This is a usability proposal based on the local operating context and requires validation with representative users. | User acceptance sessions with Arabic-speaking users; test forms, tables, search, and validation messages. | Proposed | BO-06 | — | Provisional BA recommendation only; the source assessment does not explicitly prescribe Arabic UI support. Validate language and usability scope with representative users.
NFR-008 | Offline resilience | Proposed field workflow must preserve unsynchronised entries, show pending sync state, and avoid duplicate records after retry. | NF | Must | Mr. Walid / Assessment §§2.3, 2.5 — connectivity is unreliable in village locations; offline capability is proposed, with device/security/synchronisation design open under OI-11. | Field test with connectivity disabled and restored; compare locally saved and central records. | Needs decision / validation | BO-06 | — | Provisional BA recommendation only and conditional on approved scope/feasibility. Validate device, security, local storage, retry, conflict and synchronisation design under OI-11.
NFR-009 | Low bandwidth | Common case actions must provide a clear pending/success/failure outcome on slow or unstable links and allow a user to retry safely. | NF | Should | Assessment §§2.3, 2.5 notes weak/inconsistent internet; low-bandwidth behaviour is a proposed operational requirement. No measurable threshold is provided. | Test on a simulated degraded connection; no silent record loss or duplicate submission. | Proposed | BO-06 | — | Provisional BA recommendation only; validate thresholds and degraded-network test conditions with IT and field users.
NFR-010 | GIS integrity | Preserve source coordinate-reference metadata; all transformation parameters must be approved and logged. No fixed positional accuracy threshold is adopted until validated by the Survey Authority. | NF | Must | Assessment §2.3 — Egypt 1907 / Red Belt and WGS 84 / UTM 36N data are described, with shifts of tens of metres; OI-04 requires approved transformation/accuracy validation. | Compare transformed layers against approved control data and record residuals and exceptions. | Needs decision / validation | BO-03 | OI-04 | Provisional BA recommendation only. Preserve CRS metadata and require approved transformation QA; no fixed positional tolerance is approved. Resolve OI-04.
NFR-011 | Interfaces | Any API or exchange mechanism must use an interface specification, owner, permissions, error handling, and support model agreed with the counterpart. | NF | Could | Assessment §2.5 — Civil Registry integration requires ministry approval; utility verification is conditional on counterpart, security and data-sharing decisions under OI-09. | Interface contract and end-to-end test after approval. | Needs decision / validation | BO-05; BO-07 | OI-09 | Provisional BA recommendation only because external interfaces are conditional on approval, counterpart agreement, security and data-sharing decisions under OI-09.
NFR-012 | Rule change | Tariffs and approved business rules should be configurable with effective date, approver, and audit history where supported by governance. | NF | Should | Assessment §2.4 — special street rates exist and extension-area tariffs are not set; configurable rule governance is proposed and requires policy/finance approval. | Change a test rate/rule in a controlled environment and verify history and recalculation behaviour. | Proposed | BO-05; BO-07 | — | Provisional BA recommendation only; configurable rules depend on approved tariff/policy governance and change permissions.
NFR-013 | Privacy | Collect and expose only applicant information needed for the approved process; external verification must return only agreed fields. | NF | Must | Assessment §§2.2.B, 2.3 includes national ID, ownership documents, photos and finance records, plus a data-residency constraint; specific privacy controls require IT/Legal validation. | Data inventory, role access tests, and privacy review before external exchange. | Needs decision / validation | BO-07 | — | Provisional BA recommendation only; specific privacy/security controls require validation by IT/Legal. Do not infer unprovided legal standards.
NFR-014 | Accessibility / assisted service | The design must not assume all applicants can use the internet; define the approved assisted channel and usable fallback. | NF | Must | Mr. Sayed versus Eng. Hesham, Assessment §2.5 — some applicants are elderly or cannot use the internet, while the sponsor prefers a portal; assisted-channel design remains open under OI-09. | Complete an assisted registration with representative users and compare records with online intake when available. | Needs decision / validation | BO-06 | OI-09 | Provisional BA recommendation only, based on the explicit conflict between portal preference and applicants who cannot reliably use online services. Confirm assisted-channel design under OI-09.

## Objectives & KPIs
BVDRS ¦ Business Objectives, KPIs & Capacity Check
Objectives and baselines derived from the company assessment. Targets not approved by the source are explicitly marked TBD. Capacity calculation is illustrative and depends on OI-01.
Objective ID | Business Objective | Baseline / Current Situation | Stakeholder Statement / Evidence | KPI / Target Treatment | Open Issue(s)
BO-01 | Improve detection and triage of potential new building violations | Current: quarterly 50 cm imagery; 4 GIS analysts perform manual comparison in ArcGIS Pro over about 6 weeks per quarter. Approx. 6,200 new violations were detected last year. | Sponsor requests weekly automatic detection; GIS lead says current imagery arrives every three months and weekly imagery needs a new contract/budget. | No approved target yet. Baseline cadence remains quarterly until imagery supply and funding are decided. | OI-03
BO-02 | Manage reconciliation applications end to end with visible status and accountable handoffs | Approx. 38,000 pending applications and approx. 1,500 new applications per month. Citizens return weekly asking for status. | Sayed: citizens return weekly asking “what happened to my file?” | Define a measurable case-status service target during discovery; no unapproved SLA included. | OI-01; OI-10; OI-12
BO-03 | Improve spatial locating, screening, and GIS data reliability | About 60% of buildings in informal areas/villages lack reliable parcel geometry; older and newer layers use different coordinate systems and shifts of tens of metres are reported. | Mona: engineers spend half their time finding buildings and wants location capture on a map. Ahmed: layers do not line up due to coordinate systems. | Define baseline and measurable target after layer QA and Survey Authority validation. | OI-04
BO-04 | Give leadership and operations a reliable view of backlog, throughput, collections, and follow-up | 3 committees x approx. 80 files per weekly meeting = approx. 240 files/week current stated committee throughput. | Hesham requests a map dashboard covering violations by district, applications, collections, and removals. | Dashboard definitions and targets to be approved. The six-month target requires capacity decisions. | OI-01
BO-05 | Improve tariff, fee, deposit, and instalment traceability | Finance calculates manually. Payment can be full or in instalments up to 36 months. Finance reports no current way to follow up late payments. Extension-area rates are not set; special street rates may vary. | Nagwa: many citizens pay in instalments; there is no way to follow up late payments. Deposit refund treatment is disputed. | Track approved tariffs and payments; exact deposit/refund, arrears, and certificate rules require approval. | OI-05; OI-06; OI-08
BO-06 | Provide accessible service under weak-connectivity conditions | Two technical centres and most village field locations have weak or unstable internet; applicants may be elderly or represented by lawyers/agents. | Sayed says online-only will not work. Walid says village-office internet goes down often. | Channel policy, permitted devices, and offline targets require confirmation. | OI-09; OI-11
BO-07 | Strengthen the auditability of regulatory decisions and formal follow-up | Current process relies on paper reports, local Excel sheets, paper appeals, and letters to utility companies. | Adel: appeal can be filed within 30 days from notification; removal decisions require formal notice before execution. | Define authoritative notification evidence, appeal effect, and authorised follow-up workflow before configuring timers/actions. | OI-07; OI-08
Illustrative Operational Capacity Check — validate assumptions before using as a committed target
Input / Metric | Value | Unit / Formula | Source / Calculation | Interpretation / Caveat | Status
Pending reconciliation applications | 38000 | applications | Assessment §2.3 | Approximate current backlog; scope/population must be reconciled with paper archive. | Source-stated approximate
New applications received | 1500 | applications / month | Assessment §2.3 | Assumes intake continues during the illustrative six-month horizon. | Source-stated approximate
Planning horizon | 6 | months | Sponsor statement / Assessment §2.5 | Sponsor commitment stated as backlog decided within six months; interpretation needs confirmation. | OI-01
Weeks in planning horizon | 26 | weeks | Illustrative assumption | Approximate six-month comparison window; confirm exact operational calendar. | Derived assumption
Reconciliation committees | 3 | committees | Assessment §2.3 | Each committee meets once a week. | Source-stated
Files per committee per meeting | 80 | files / committee / week | Assessment §2.3 | Stated approximate throughput per committee meeting. | Source-stated approximate
Illustrative workload incl. new intake | 47000 | applications | Backlog + new applications/month × months | Assumes all 1,500 monthly incoming applications are within the six-month decision target; verify this interpretation. | Calculated; OI-01
Required decisions per week | 1807.6923 | applications / week | Illustrative workload ÷ weeks | Derived required rate under assumptions above; not an approved operational target. | Calculated; OI-01
Current committee capacity per week | 240 | applications / week | Committees × files per meeting | Assumes all three committees meet weekly and figures are comparable. | Calculated from source figures
Weekly capacity gap | 1567.6923 | applications / week | Required decisions/week − current capacity | Illustrative gap; not a probability of failure. | Calculated; OI-01
Current capacity / required capacity | 13.28% | percentage | Current capacity ÷ required decisions | Relative coverage of illustrative required workload. | Calculated; OI-01
Required throughput multiple | 7.5321 | x current capacity | Required decisions/week ÷ current capacity/week | Additional operating capacity or a revised plan is needed if assumptions hold. | Calculated; OI-01
Incoming applications average per week | 346.1538 | applications / week | Monthly intake × 12 ÷ 52 | Illustrative average; current stated capacity may be lower than new inflow if measures are comparable. | Calculated from source figures

## Traceability Matrix
BVDRS ¦ Requirements Traceability Matrix
26 meaningful source links (exceeds the required minimum of 10). Each row connects a specific requirement to a business objective and a named stakeholder statement/current-state evidence. An explicit objective or source gap remains an Open Issue rather than being inferred as approved.
Trace ID | Requirement ID | Objective ID | Business Objective | Stakeholder / Source | Stakeholder Statement / Evidence | Traceability Rationale | Source Reference | Relationship Status | Open Issue(s)
TR-001 | FR-DET-001 | BO-01 | Improve detection and triage of potential new violations | Eng. Ahmed / Eng. Hesham | Ahmed: imagery arrives every three months; weekly imagery would need a new contract and budget. Hesham requests weekly automatic detection. | Registering image provenance supports controlled comparison and makes imagery cadence/source visible. | Assessment §§2.2.A, 2.5; FR source/status in BRD | Direct need; future cadence unresolved | OI-03
TR-002 | FR-DET-003 | BO-01 | Improve detection and triage of potential new violations | Eng. Hesham / Eng. Ahmed | Hesham requests automatic satellite-image detection; Ahmed identifies quarterly input cadence and budget constraints. | Comparison capability supports candidate generation but does not commit to weekly delivery or an SLA. | Assessment §§2.2.A, 2.5 | Proposed capability | OI-03
TR-003 | FR-DET-004 | BO-01 | Improve detection and triage of potential new violations | GIS Unit / current AS-IS | Current GIS analysts visually compare imagery, mark suspected buildings, and dispatch locations for field checks. | Human review gate preserves analyst validation before field dispatch. | Assessment §2.2.A | Proposed control grounded in current workflow
TR-004 | FR-FLD-001 | BO-03 | Improve spatial locating, screening, and GIS data reliability | Eng. Mona, Head of Engineering and Planning | Mona: no decision can be made without a site inspection by an engineer. | Assigned inspection tickets support the stated inspection step; they do not remove the site-visit requirement. | Assessment §§2.2.A, 2.5 | Source-supported business need; system design proposed | OI-02
TR-005 | FR-FLD-004 | BO-06 | Provide accessible service under weak-connectivity conditions | Mr. Walid, Governorate IT Manager | Walid: internet in village offices goes down often; field engineers cannot depend on it. | Offline capture is a proposed response; device/security/sync design needs validation. | Assessment §§2.3, 2.5 | Proposed; technical validation required | OI-11
TR-006 | FR-APP-001 | BO-02 | Manage applications end to end with visible status and accountable handoffs | Current reconciliation process | Owner or lawyer/agent with a power of attorney visits one of four technical centres with a paper file. | Unique case references provide a consistent way to track a case across offices. | Assessment §2.2.B | Proposed capability | OI-09
TR-007 | FR-APP-002 | BO-02 | Manage applications end to end with visible status and accountable handoffs | Current reconciliation process | The paper file includes ownership documents, national ID, structural safety report, building photos, and a site sketch. | The requirement structures the documented checklist; any document-policy change requires approval. | Assessment §2.2.B | Source-supported document types; digital handling proposed
TR-008 | FR-APP-004 | BO-03 | Improve spatial locating, screening, and GIS data reliability | Eng. Mona, Head of Engineering and Planning | Mona: if the citizen could point to the building on a map when applying, it would save a lot of time finding it. | Map-based location capture is proposed; it must not imply a verified cadastral parcel where none exists. | Assessment §2.5; §2.3 | Proposed
TR-009 | FR-APP-005 | BO-02 | Manage applications end to end with visible status and accountable handoffs | Mr. Sayed, Technical Centres Manager | Sayed: citizens come back every week asking “what happened to my file?” | Status history and authorised status visibility address transparency and handoff tracking. | Assessment §2.5 | Proposed
TR-010 | FR-APP-006 | BO-06 | Provide accessible service under weak-connectivity conditions | Eng. Hesham / Mr. Sayed | Hesham wants portal-based online applications; Sayed says many applicants are elderly or cannot use the internet and online-only will not work. | The channel requirement remains subject to resolving the sponsor/operations conflict. | Assessment §2.5 | Decision required | OI-09
TR-011 | FR-GIS-002 | BO-03 | Improve spatial locating, screening, and GIS data reliability | Eng. Mona, Head of Engineering and Planning | Mona asks to identify automatically whether a building is in a zone where reconciliation is not allowed. | Automated layer screening supports review; it does not independently make the final legal decision. | Assessment §2.5; §2.2.B | Source-supported restriction categories; final decision remains human
TR-012 | FR-GIS-004 | BO-03 | Improve spatial locating, screening, and GIS data reliability | Eng. Ahmed, GIS Unit Head | Ahmed: half the layers do not line up due to different coordinate systems; buildings appear shifted by tens of metres. | CRS metadata and transformation QA are necessary before trusting spatial intersections. | Assessment §2.3; §2.5 | Decision required for transformation/accuracy | OI-04
TR-013 | FR-GIS-005 | BO-03 | Improve spatial locating, screening, and GIS data reliability | GIS / cadastral context | About 60% of buildings in informal areas and villages have no reliable parcel geometry; Ahmed notes parcels are absent in villages. | A provisional location can support tracking without misrepresenting it as an authoritative parcel. | Assessment §2.3; §2.5 | Proposed | OI-04
TR-014 | FR-WF-002 | BO-02 | Manage applications end to end with visible status and accountable handoffs | Current reconciliation committee workflow | The committee decides to approve, reject, or request more documents. | The stated outcomes should be explicitly recorded and routed. | Assessment §2.2.B | Source-supported outcome set; workflow detail requires confirmation | OI-12
TR-015 | FR-WF-005 | BO-07 | Strengthen the auditability of regulatory decisions and formal follow-up | Mr. Adel, Legal Counsel | Adel: an applicant has 30 days from notification to file an appeal. | The system should track appeal records and notification evidence without assuming an automatic stay or timer trigger. | Assessment §2.5 | Appeal window source-supported; effect and trigger unresolved | OI-07
TR-016 | FR-WF-006 | BO-07 | Strengthen the auditability of regulatory decisions and formal follow-up | Mr. Adel, Legal Counsel | Adel: removal decisions require formal notice before execution. | Record authorised follow-up and notice status; do not automate removal or invent the workflow. | Assessment §2.5 | Source-supported principle; detailed workflow unresolved | OI-07
TR-017 | FR-FIN-001 | BO-05 | Improve tariff, fee, deposit, and instalment traceability | Finance tariff table / Finance Manager | Finance provides indicative zone rates; new urban extension rates are not yet set. | Versioned approved tariff data supports accountable fee calculation and prevents silent rate changes. | Assessment §2.4 | Tariff values illustrative; approval/effective dates needed | OI-05
TR-018 | FR-FIN-002 | BO-05 | Improve tariff, fee, deposit, and instalment traceability | Finance | Finance notes that the pricing committee sometimes sets a special rate for a specific street different from its zone class. | Special rates require an approval reference and precedence rules. | Assessment §2.4 | Source-supported variation; approval mechanism to define | OI-05
TR-019 | FR-FIN-003 | BO-05 | Improve tariff, fee, deposit, and instalment traceability | Finance tariff table | New urban extension areas have no rate set by the pricing committee. | The proposed control holds finalisation instead of guessing a rate. | Assessment §2.4 | Proposed control | OI-05
TR-020 | FR-FIN-005 | BO-05 | Improve tariff, fee, deposit, and instalment traceability | Mrs. Nagwa, Finance Manager | Nagwa says the deposit is non-refundable, but rejected applicants demand it back. | Record deposit and disputes; do not auto-approve or auto-deny refunds until a policy decision is made. | Assessment §§2.4, 2.5 | Policy conflict open | OI-06
TR-021 | FR-FIN-006 | BO-05 | Improve tariff, fee, deposit, and instalment traceability | Mrs. Nagwa, Finance Manager | Nagwa says many citizens pay in instalments and there is no current way to follow up late payments. | A ledger and due-date tracking capability responds to the stated control gap; arrears consequences need approval. | Assessment §§2.4, 2.5 | Source-supported need; detailed rules open | OI-08
TR-022 | FR-CERT-003 | BO-07 | Strengthen the auditability of regulatory decisions and formal follow-up | Eng. Khaled / Mr. Walid | Khaled wants online certificate verification before meter installation; Walid says civil-registry integration needs ministry approval and data must stay in the Governorate data centre. | Utility verification must remain conditional on counterpart, security, hosting, and data-sharing approvals. | Assessment §§2.3, 2.5 | Conditional / decision required | OI-09
TR-023 | FR-REP-001 | BO-04 | Give leadership and operations a reliable view of backlog, throughput, collections, and follow-up | Eng. Hesham, Sponsor | Hesham asks for a map dashboard of violations by district, applications, collections, and removals. | The dashboard should define data sources, refresh and permissions; removals reflect recorded authorised events only. | Assessment §2.5 | Source-supported need; metric definitions to agree | OI-01
TR-024 | FR-DAT-003 | BO-02 | Manage applications end to end with visible status and accountable handoffs | Mr. Sayed / source key facts | Sayed asks what happens to approximately 40,000 paper files; assessment separately lists approximately 38,000 pending applications. | Migration scope must distinguish the two populations and reconcile any overlap before loading. | Assessment §§2.3, 2.5 | Decision required | OI-10
TR-025 | NFR-010 | BO-03 | Improve spatial locating, screening, and GIS data reliability | Eng. Ahmed, GIS Unit Head | Existing layers use Egypt 1907 / Red Belt and WGS 84 / UTM 36N; imagery arrives in WGS 84; shifts of tens of metres are reported. | Preserve CRS metadata and require approved transformation/QA. No fixed positional tolerance is approved. | Assessment §§2.3, 2.5 | Needs Survey Authority validation | OI-04
TR-026 | NFR-014 | BO-06 | Provide accessible service under weak-connectivity conditions | Mr. Sayed, Technical Centres Manager | Sayed says many applicants are elderly or cannot use the internet; most files are submitted by lawyers or agents. | The service design should not assume internet-only access; the supported channel model must be approved. | Assessment §2.5 | Decision required | OI-09

## User Stories
BVDRS ¦ User Stories & Gherkin Acceptance Criteria
Five assessment-required user stories, each with an explicit As a / I want / So that statement and Given / When / Then acceptance criteria. Stories are proposed examples, not approved scope.
Story ID | Title | User Story (As a / I want / So that) | Given | When | Then | Linked Requirements | Status / Dependency | Primary Actor
US-01 | Review an imagery candidate | As a GIS analyst, I want to review detected candidate changes with their source imagery, so that I can validate or dismiss candidates before field dispatch. | An imagery pair has passed ingestion checks. | The analyst opens the comparison results. | The system displays candidate locations linked to the source images and records the analyst's confirm/dismiss decision, user, time, and reason. | FR-DET-003; FR-DET-004 | Proposed; imagery automation/frequency subject to OI-03 | GIS Unit Head / GIS Analyst
US-02 | Record a field inspection with weak connectivity | As a field engineer, I want to record an assigned visit even when the connection is unavailable, so that site evidence is not lost because of connectivity. | An assigned ticket and available site information are saved locally. | The engineer records the visit outcome, notes, area estimate, and available photos offline. | The record remains marked pending synchronisation and is safely submitted after connectivity returns without creating a duplicate. | FR-FLD-001; FR-FLD-002; FR-FLD-003; FR-FLD-004; NFR-008; NFR-009 | Proposed; device, security and offline design require validation (OI-11) | Field Engineer / IT / Engineering
US-03 | Register a reconciliation application | As a technical-centre clerk, I want to register an application and its document checklist, so that the case can be tracked across the offices. | An owner or authorised agent presents an application. | The clerk records the party, documents, intake channel, and any deposit evidence under the approved intake policy. | The system assigns a unique case reference and displays received/missing documents and the next responsible queue. | FR-APP-001; FR-APP-002; FR-APP-003; FR-APP-005; FR-FIN-005 | Proposed system capability; intake/deposit policy dependencies remain open (OI-06; OI-09) | Technical-Centre Clerk / Sayed / Finance
US-04 | Record a committee decision | As a committee secretary, I want to record the authorised outcome and reasons, so that the case history and follow-up action are auditable. | A case is scheduled for committee review. | The authorised committee records approve, reject, or request-more-documents. | The system records the outcome, date, responsible committee/authorised user, reasons and related evidence, and routes the case according to the approved workflow. | FR-WF-001; FR-WF-002; FR-WF-003; FR-WF-004; NFR-006 | Proposed system capability; routing and reason rules need validation (OI-12) | Committee Secretariat / Engineering / Legal
US-05 | Prevent a fee calculation using an unknown rate | As a finance officer, I want the system to identify when no approved rate exists, so that an applicant is not charged using an invented tariff. | A case belongs to an extension area without an approved tariff. | Finance attempts to finalise the fee. | The system holds finalisation, displays the missing-rate issue, and records the authorised rate once approved rather than silently applying a default. | FR-FIN-001; FR-FIN-002; FR-FIN-003; FR-FIN-004 | Proposed control grounded in the missing-rate problem; rate approval is required (OI-05) | Finance / Pricing Committee

## Business Rules
BVDRS ¦ Business Rules Register
16 rules taken from the revised BRD. The status column deliberately separates source-stated facts from proposed controls and decisions requiring an authorised policy owner.
Rule ID | Rule Name | Rule Statement | Evidence / Authority | Status | Open Issue(s)
BR-01 | Phase-one geography | The initial scope applies to Madinat Al-Wadi and surrounding villages identified for Phase 1. | Assessment 2.1 | Source-supported | —
BR-02 | Human inspection | The current process includes an engineer site inspection; the Engineering Head states that decisions cannot be made without one. No Fast-Track exemption is confirmed. | Assessment 2.2.B; Mona | Source-supported current practice / proposed baseline | —
BR-03 | Spatial restrictions | Relevant checks include urban boundary, agricultural land, Nile protection, heritage, and airport height restrictions. | Assessment 2.2.B | Source-supported categories; rule details to validate | —
BR-04 | GIS decision limit | A spatial match is screening evidence; final eligibility must be determined by the authorised engineering/committee/legal process. | BA control to preserve accountability | Proposed control | —
BR-05 | Fee calculation basis | Finance's current calculation is violating area multiplied by the applicable price per square metre, with the down payment deducted from the payable balance. | Assessment 2.2.B and 2.4 | Source-supported description | —
BR-06 | Zone tariffs | Illustrative base rates are Zone A EGP 1,200/m2, Zone B EGP 800/m2, Zone C EGP 450/m2, and Zone D EGP 150/m2. | Finance table, assessment 2.4 | Illustrative schedule; approval/effective dates required | —
BR-07 | Street override | A special street rate set by the Pricing Committee may differ from the general zone class rate. | Finance note, assessment 2.4 | Source-supported; approval mechanism to define | —
BR-08 | Unpriced extensions | New urban extension rates have not been set. A proposed control is to hold calculation until an authorised rate is available rather than use a guessed rate. | Assessment 2.4 | Source-supported gap / proposed control | —
BR-09 | Down payment | Payment terms state a 25% down payment at application. Finance describes it as non-refundable, while rejected applicants demand refunds. | Assessment 2.4 and Nagwa interview | Timing/refund policy conflict; OI-06 | OI-06
BR-10 | Instalments | Remaining amounts may be paid in full or in instalments over up to 36 months. | Assessment 2.4 | Source-supported; detailed schedule and arrears rules to approve | —
BR-11 | Committee outcomes | The committee may approve, reject, or request additional documents. | Assessment 2.2.B | Source-supported | —
BR-12 | Appeal window | A rejected applicant may file an appeal within 30 days from notification. The notification evidence and legal effect of a pending appeal are not defined in the case. | Assessment 2.5 and Adel interview | Window source-supported; trigger/effect open | —
BR-13 | Removal notice | Removal decisions require formal notice before execution. The detailed authorisation and execution workflow is not provided. | Adel interview, assessment 2.5 | Source-supported principle; workflow open | —
BR-14 | Imagery cadence | Current imagery is quarterly at 50 cm resolution. Weekly imagery would require a new contract and additional budget according to the GIS lead. | Assessment 2.2.A / Ahmed | Source-supported current state; future cadence open | —
BR-15 | Civil registry | National ID data is held by the civil registry; no integration exists today and ministry approval is required. | Assessment 2.3 / Walid | Source-supported constraint | —
BR-16 | Spatial reference and cadastral gaps | Older layers use Egypt 1907 / Red Belt, newer layers use WGS 84 / UTM 36N, and imagery arrives in WGS 84. Around 60% of buildings in informal areas/villages lack reliable parcel geometry. | Assessment 2.3 / Ahmed | Source-supported; transformation/accuracy decisions open | —

## Open Issues
BVDRS ¦ Open Issues & Decision Log
12 unresolved matters explicitly carried forward from the BRD. No clarification response was received. The log is designed for stakeholder ownership and closure before requirements baseline/sign-off.
Issue ID | Topic | Decision Required | Why It Matters / Impact | Decision Owner(s) | Priority | Status | Affected Requirements / Objectives | Interim Treatment
OI-01 | Six-month backlog target and capacity | Does the six-month target include new applications, and what capacity increase is authorised? | Determines throughput KPI, resource plan, committee workflow, rollout assumptions, and sponsor commitment. | Hesham; committee owners | Critical | Open — clarification not received | FR-REP-001; FR-REP-002; FR-WF-001; BO-02; BO-04 | Show derived capacity gap; do not claim feasibility.
OI-02 | Inspection requirement and exceptions | Is site inspection mandatory for every application, and who may authorise exceptions? | Controls TO-BE process, prioritisation, inspection workload, and any proposed Fast-Track route. | Mona; Legal; committees | High | Open — clarification not received | FR-FLD-001; FR-WF-001; BO-03 | Inspection remains the baseline; no exception enabled.
OI-03 | Imagery frequency and funding | Is weekly imagery required, budgeted, and available? Are drones or hotspot imagery acceptable? | Determines data supply, technical architecture, achievable detection frequency, and delivery cost. | Hesham; Ahmed; Procurement | High | Open — clarification not received | FR-DET-001; FR-DET-002; FR-DET-003; BO-01 | Use quarterly 50 cm imagery as current baseline; alternatives are proposals.
OI-04 | Coordinate transformation and accuracy | What coordinate transformation and positional accuracy are approved? | Layer shifts affect screening, site finding, migration, and trust in spatial results. | Ahmed; Survey Authority; Walid | High | Open — clarification not received | FR-GIS-001; FR-GIS-004; NFR-010; BO-03 | Preserve CRS metadata; no fixed accuracy target or unapproved transformation.
OI-05 | Tariff approval and rate overrides | Who approves missing extension-area tariffs and street-specific rate overrides, and with what effective dates? | Incomplete rates can block billing and create incorrect fee assessments. | Finance; Pricing Committee | High | Open — clarification not received | FR-FIN-001; FR-FIN-002; FR-FIN-003; FR-FIN-004; US-05; BO-05 | Hold fee finalisation until an authorised rate exists.
OI-06 | Deposit timing and refund treatment | What is the approved timing and refund treatment of the 25% deposit, especially on rejection or withdrawal? | Finance says non-refundable while rejected applicants demand refunds; pre-screening/deposit order is not consistently defined. | Nagwa; Legal; Sponsor | High | Open — clarification not received | FR-FIN-005; FR-APP-003; US-03; BO-05 | Record deposit and refund request; do not auto-refund or auto-deny.
OI-07 | Appeal trigger, evidence, and legal effect | What event starts the 30-day appeal period, what proves notification, and what is the appeal’s effect on removal? | Avoids inventing an appeal timer, legal stay, or premature enforcement path. | Adel; Legal authority; Committee | High | Open — clarification not received | FR-WF-005; FR-WF-006; NFR-006; BO-07 | Capture dates/evidence; no automatic stay or executable timer.
OI-08 | Certificate issuance and arrears | When can a certificate be issued if fees are paid by instalments, and can arrears change certificate status? | Affects certificate states, utility checks, finance reports, and applicant communications. | Nagwa; Adel; Sponsor | High | Open — clarification not received | FR-CERT-001; FR-CERT-002; FR-CERT-003; FR-FIN-006; BO-05; BO-07 | Track payment and certificate status separately; no 60-day suspension rule.
OI-09 | Intake channel and integration scope | Which intake channel and external integrations are approved (national portal, civil registry, payment provider, utilities)? | Drives identity verification, data exchange, hosting, security, service accessibility, and cost. | Hesham; Walid; Ministry; providers; utilities | High | Open — clarification not received | FR-APP-006; FR-CERT-003; NFR-011; NFR-014; BO-06 | Keep external integrations conditional; preserve assisted intake in proposed model.
OI-10 | Backlog versus paper archive population | Are the 38,000 pending cases and 40,000 paper archive files distinct, overlapping, or differently defined? | Prevents double counting, migration mistakes, incorrect backlog measures, and under/over-scoping. | Sayed; Walid; data owners | High | Open — clarification not received | FR-DAT-001; FR-DAT-002; FR-DAT-003; BO-02 | Inventory and reconcile populations before migration.
OI-11 | Field devices and offline operating model | Which field devices, mobile management, photography rules, offline storage, and support model are permitted? | Required for an implementable offline workflow and acceptable evidence handling. | Walid; Mona; GIS; Procurement | Medium-High | Open — clarification not received | FR-FLD-004; FR-FLD-005; NFR-008; NFR-009; BO-06 | Treat offline work as proposed pending proof of concept.
OI-12 | Missing-document routing and resubmission | Where do incomplete documents return, who receives them, and where does committee review resume? | Needed for correct loop design, ownership, service status, and user notification. | Sayed; Committee Secretariat; Legal | Medium-High | Open — clarification not received | FR-WF-003; FR-WF-001; BO-02 | Show provisional route and mark it for confirmation.

## Overview
Building Violations Detection & Reconciliation System (BVDRS)
Requirements workbook ¦ Prepared by Muhammad Amjad Karara ¦ Status: Draft for review — not approved baseline
Workbook Contents & Quality Gate
Sheet | Purpose | Main content | How to use
Requirements Register | Main requirement source of truth | 42 functional + 14 non-functional requirements | Filter by module, priority, status, objective, or Open Issue.
Traceability Matrix | Evidence links | 26 links to business objectives and stakeholder statements | Use Trace IDs to explain why each requirement exists.
User Stories | User-centred examples | 5 stories with Given / When / Then criteria | Use in the defense to explain expected behaviour and testability.
Objectives & KPIs | Goals, baselines, and capacity math | 7 objectives and an illustrative capacity check | Capacity outputs depend on OI-01 assumptions and are not an approved operating plan.
Business Rules | Policy/rule inventory | 16 rules with evidence and status | Do not configure rules labelled proposed or open until approved.
Open Issues | Decision log | 12 unresolved questions with owner/priority/interim treatment | Close or formally accept each issue before a signed-off baseline.
Completeness Snapshot
Check | Count / Status |  | Important use notes
All requirements | 56 |  | 1. The original company assessment is the authority; AI drafts and proposed designs are not automatically approved.
Functional requirements (F) | 42 |  | Priority values for NFRs are provisional BA recommendations, not formal approvals. Numeric performance, capacity, availability and recovery targets require validation; no unconfirmed legal effect is inferred for appeals.
Non-functional requirements (NF) | 14 |  | 3. No legal effect is inferred for an appeal beyond the stated 30-day filing window and formal notice principle.
Traceability links | 26 |  | Priorities are recommendations for assessment review. Weekly imagery, intake channel, tariff gaps, deposit/refund policy, certificate conditions, integrations and archive scope remain decision points.
User stories | 5 |  | 5. Capacity calculations are illustrative and must be defended with their assumptions; a relative capacity gap is not a probability of failure.
Business rules | 16
Open issues | 12